## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Predicting Student Placement Status Using Machine Learning for Academic and Career Support
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2025-12-20
EXPECTED COMPLETION DATE | 2026-01-31
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | The objective of this project is to design and implement a supervised machine learning–based classification system that predicts whether a student will be Placed or Not Placed based on academically and professionally relevant features such as CGPA, speaking skills, and machine learning knowledge. The system aims to support early academic and career interventions by educational institutions.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Educational institutions face challenges in identifying students who require early career support. Manual evaluation methods are time-consuming and often subjective. By using machine learning, institutions can gain data-driven insights into student placement readiness. This project provides a cost-effective, scalable, and objective solution that improves placement planning, reduces risk of student underperformance, and enhances overall employability outcomes.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 1. Achieve a working supervised ML classification model 2. Improve recall for identifying placement-ready students 3. Ensure domain-driven feature selection and ethical modeling 4. Deliver predictions for unseen student data 5. Complete the project within the defined schedule and resources
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Cleaned and preprocessed datasets 2. Trained Random Forest classification model 3. Model evaluation metrics (Accuracy, Precision, Recall, F1-score, Confusion Matrix) 4. Feature importance and data visualizations 5. Excel file containing predicted placement status 6. Complete project documentation set
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | 1. Data cleaning and preprocessing 2. Missing value handling 3. Domain-driven feature selection 4. Feature engineering (Academic Readiness Score) 5. Training and evaluation of Random Forest classifier 6. Visualization of model performance 7. Excel-based prediction output
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | 1. Real-time system deployment 2. Web or mobile application development 3. Resume parsing or interview analysis 4. Deep learning or neural network models 5. Integration with live institutional databases
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Student Intern (Individual Project)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Google Colab (development environment) Python and ML libraries (pandas, numpy, scikit-learn, matplotlib, seaborn) Academic mentor / evaluator guidance
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Software tools: Free / Open Source Cloud resources: Free tier (Google Colab) Development cost: N.A.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Student Intern (Project Owner)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Academic Institution Internship Program Coordinators Faculty Mentors Career Counselors
END CUSTOMER (Mention the client name.) | Educational Institutions and Students
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Class imbalance affecting prediction accuracy 2. Noise or missing values in dataset 3. Limited number of strongly predictive features
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. Academic performance and skills influence placement outcomes 2. Historical data patterns are representative of future trends 3. Students with similar profiles exhibit similar placement probabilities
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. Fixed internship duration 2. Use of predefined dataset 3. Restricted to specified tools and technologies 4. No real-time deployment
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date: 12-24-2025 Requirement gathering is marked complete after submission of the SRS document.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date: 12-29-2025 Planning phase is completed after WBS, project schedule, and RAID logs.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 01-03-2026 Design stage is complete after submission of design specifications.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 01-12-2026 Development stage is complete after model implementation and feature engineering.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date: 01-18-2026 Testing stage is complete after evaluation metrics and test reports.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date: 01-24-2026 Deployment stage is complete after generation of Excel output and final predictions.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date: 01-31-2026 Project closure is complete after submission of final report, lessons learnt log, and documentation.