## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Aquib Zakir Ahmad
Document Created On: | 2026-01-06
Version: | 5
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## PROJECT PLAN
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Student Placement Prediction using XGBoost |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Aquib Zakir Ahmad
PROJECT DELIVERABLE | Global Professional Internship
PROJECT SCOPE
PROJECT START DATE | 12-24-2025
PROJECT END DATE | 01-31-2026
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify problem statement (placement prediction) | Self | 2025-12-24 | 2025-12-24 | 1 | COMPLETED
| 1.2 Collect dataset + understand attributes | Self | 2025-12-24 | 2025-12-24 | 1 | COMPLETED
| 1.3 Create Project Charter | Self | 2025-12-24 | 2025-12-24 | 1 | COMPLETED
| 1.4 Requirement gathering + SRS submission | Self | 2025-12-24 | 2025-12-24 | 1 | COMPLETED
2 Planning
| 2.1 Prepare WBS | Self | 2025-12-25 | 2025-12-26 | 2 | COMPLETED
| 2.2 Create Project Schedule | Self | 2025-12-27 | 2025-12-28 | 2 | COMPLETED
| 2.3 Create RAID Log | Self | 2025-12-29 | 2025-12-29 | 1 | COMPLETED
3 Execution
| 3.1 Design (workflow + architecture + wireframe) | Self | 2025-12-30 | 2026-01-03 | 5 | COMPLETED
| 3.2 Development (data prep + training pipeline) | Self | 2026-01-04 | 2026-01-12 | 9 | COMPLETED
| 3.2.1 Data preprocessing + missing value handling | Self | 2026-01-04 | 2026-01-06 | 3 | COMPLETED
| 3.2.2 Semi-supervised label filling | Self | 2026-01-07 | 2026-01-08 | 2 | COMPLETED
| 3.2.3 Feature scaling + SMOTE balancing | Self | 2026-01-09 | 2026-01-10 | 2 | COMPLETED
| 3.2.4 Final XGBoost model training | Self | 2026-01-11 | 2026-01-12 | 2 | COMPLETED
| 3.3 Testing | Self | 2026-01-13 | 2026-01-18 | 6 | COMPLETED
| 3.3.1 Evaluation metrics (Acc, Prec, Recall, F1) | Self | 2026-01-13 | 2026-01-15 | 3 | COMPLETED
| 3.3.2Confusion matrix + validation checks | Self | 2026-01-16 | 2026-01-18 | 3 | COMPLETED
4 Deployment
| 4.1 Test dataset prediction | Self | 2026-01-19 | 2026-01-21 | 3 | COMPLETED
| 4.2 Export output to Excel | Self | 2026-01-22 | 2026-01-23 | 2 | COMPLETED
| 4.3 Final result verification | Self | 2026-01-24 | 2026-01-24 | 1 | COMPLETED
5 Closure
| 5.1 Prepare final report | Self | 2026-01-25 | 2026-01-28 |  | COMPLETED
| 5.2 Prepare lessons learned log | Self | 2026-01-29 | 2026-01-30 |  | COMPLETED
| 5.3 Final submission + documentation handover | Self | 2026-01-31 | 2026-01-31 |  | COMPLETED