## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Student Placement Prediction using XGBoost |  | Project Id: | IAC-ML-PLACEMENT-2026 | Project Manager: | Self (Aquib) |  |  | Assumption | 3 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 5 |  | Last Updated date: | 2026-01-31 | Project Team Lead: | Self (Aquib) |  |  | Dependency | 4 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 14 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Missing values in Placement Status could reduce training quality. | Wrong model learning, reduced accuracy. | Use semi-supervised label filling and validate class distribution. | Self | High | 16 | Closed | Risk
2 | Risk | Class imbalance may bias model towards majority class. | Low recall for minority class (Placed). | Apply SMOTE on training data and check metrics. | Self | High | 15 | Closed | Assumption
3 | Risk | Wrong encoding/mapping of “Placed” and “Not placed”. | Model gives completely incorrect predictions. | Verify using value_counts() + sample print before encoding. | Self | Critical | 20 | Closed | Issue
4 | Risk | Overfitting due to high n_estimators or depth. | Poor performance on unseen test data. | Use controlled parameters, validate using test split metrics. | Self | Moderate | 12 | Closed | Dependency
5 | Assumption | Environment issues (XGBoost / imbalanced-learn not installed). | Delay in execution and testing. | Use pip install commands + verify imports before starting. | Self | Moderate | 10 | Closed
6 | Assumption | Dataset provided contains meaningful patterns for placement prediction. | If false, model performance will remain low. | Mention limitation in final report and suggest adding more features. | Self | Moderate |  | Closed | Open
7 | Assumption | Features CGPA, Speaking Skills, ML Knowledge are sufficient for baseline model. | Limited accuracy and recall possible. | Document future scope: internships, aptitude, projects, etc. | Self | Low |  | Closed | Closed
8 | Issue | Training and test dataset follow similar distribution. | If mismatch, predictions become unreliable. | Perform quick descriptive statistics comparison. | Self | Moderate |  | Closed
9 | Issue | ValueError occurred when only one class was present after filtering. | Model training fails. | Ensure both classes exist before split; handle missing labels first. | Self | High |  | Closed | Critical
10 | Issue | Low baseline accuracy in early run. | Model not acceptable for evaluator. | Tune hyperparameters + apply SMOTE + scaling. | Self | Moderate |  | Closed | High
11 | Dependency | Test dataset contained missing feature values. | Prediction pipeline fails or gives NaNs. | Fill missing using training median before scaling. | Self | High |  | Closed | Moderate
12 | Dependency | Availability of training and test Excel files (01_train_data.xlsx, 02_test_data.xlsx). | Project cannot start without dataset. | Keep dataset in same folder; verify file path early. | Self | Critical |  | Closed | Low
13 | Dependency | Required Python libraries: pandas, sklearn, xgboost, imblearn. | Execution blocked if missing. | Add setup section with installation steps. | Self | High |  | Closed | Negligible
14 | Dependency | Excel output required for evaluator submission. | Submission incomplete without final file. | Generate final Excel with predictions and proper column names. | Self | Moderate |  | Closed
15
16
17
18
19
20
21
22
23
24